## Sheet1
EST. END DATE: | APRIL 30, 2025 |  |  |  | HARD END DATE: | MAY 22, 2025 |  |  | PROJECT X- AUTOMATED
2026-05-13
|  |  | DEADLINE: MAY 02, 2025 | [6 empty] | Days Left: 17
Task Done: 9/32
Task ID | Task Name | Sub Task ID | Sub Task Name | Deliverables | Assignee | Estimated Hours (Days) | Plan Start Date | Act StDate Started | Plan End Date | Act End Date | Status
1 | Project Initiation | 1.1 | Define project objectives | Project scope document | Team | 1 | 2025-03-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | Done
|  | 1.2 | Project closure & documentation | Stakeholder list | John Dave Lazaga | 1 | 2025-11-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | Done
|  | 1.3 | Conduct feasibility study | Feasibility report | Dan Hermie Tameng | 1 | 03/13/2025 | 03/13/2025 | 03/14/2025 | 03/13/2025 | Done
|  | 1.4 | Create project plan | Project plan document | Team | 3 | 03/14/2025 | 03/14/2025 | 03/17/2025 | 03/16/2025 | Done
|  | 1.5 | Obtain approvals | Approved project charter | Kate Rodriguez | 4 | 03/17/2025 | 03/16/2025 | 03/20/2025 | 03/18/2025 | Done
2 | Requirement Analysis | 2.1 | Gather functional requirements | Requirement specification document | Kate Rodriguez | 2 | 03/15/2025 | 03/17/2025 | 03/19/2025 | 03/18/2025 | Done
|  | 2.3 | Define system architecture | System architecture diagram | Dan Hermie Tameng | 1 | 03/21/2025 | 03/19/2025 | 03/21/2025 | 03/20/2025 | Done
3 | Design Phase | 3.1 | Conceptual Design | Design Review, Finalization of Design | Kate Rodriguez | 2 | 2025-03-22 | 03/24/2025 | 03/27/2025 | 03/27/2025 | Done
|  | 3.2 | Database design | ERD and database schema | Dan Hermie Tameng | 2 | 2025-03-24 | 2025-03-26 | 2025-03-29 | 2025-03-29 | Done
|  | 3.3 | API design | API documentation | John Dave Lazaga | 3 | 2025-03-26 | 2025-03-28 | 2025-03-31 | 2025-03-31 | Done
|  | 3.4 | UI/UX design | Final UI/UX designs | Team | 2 | 2025-03-29 | 2025-03-31 | 2025-04-03 | 2025-04-03 | Done
|  | 3.5 | Security design | Security measures document | Dan Hermie Tameng | 3 | 2025-03-31 | 2025-04-02 | 2025-04-05 | 2025-04-05 | Done
4 | Development Phase | 4.1 | Set up development environment | Configured development tools | Dan Hermie Tameng | 4 | 2025-04-03 | 2025-04-05 | 2025-04-08 | 2025-04-08 | Done
|  | 4.2 | Frontend development (React Native) | Initial UI screens | Dan Hermie Tameng | 4 | 2025-04-07 | 2025-04-09 | 2025-04-12 | 2025-04-12 | Done
|  | 4.3 | Backend development | Working backend APIs | John Dave Lazaga | 4 | 2025-04-11 | 2025-04-13 | 2025-04-16 | 2025-04-16 | Done
|  | 4.4 | QR Code scanning implementation | Functional QR scanner module | John Dave Lazaga | 4 | 2025-04-15 | 2025-04-17 | 2025-04-20 | 2025-04-20 | Done
|  | 4.5 | GPS validation implementation | Functional GPS validation | John Dave Lazaga | 4 | 2025-04-19 | 2025-04-21 | 2025-04-24 | 2025-04-24 | Done
|  | 4.6 | Secure storage implementation | Encrypted storage module | John Dave Lazaga | 4 | 2025-04-23 | 2025-04-25 | 2025-04-28 | 2025-04-28 | Done
|  | 4.7 | Testing unit integration | Test reports | Team | 4 | 2025-04-27 | 2025-04-29 | 2025-05-02 | 2025-05-02 | Done
5 | Testing & QA | 5.1 | Functional testing | Test case reports | Team | 3 | 2025-05-01 | 2025-05-03 | 2025-05-06 | 2025-05-06 | Done
|  | 5.2 | Security testing | Security vulnerability report | Team | 3 | 2025-05-04 | 2025-05-06 | 2025-05-09 | 2025-05-09 | Done
|  | 5.3 | User acceptance testing | User feedback & approval | Team | 3 | 2025-05-07 | 2025-05-09 | 2025-05-12 | 2025-05-12 | Done
6 | Deployment | 6.1 | Prepare deployment environment | Deployment guide | Team | 3 | 2025-05-10 | 2025-05-12 | 2025-05-15 | 2025-05-15 | Done
|  | 6.2 | Deploy backend API | Hosted backend | Team | 3 | 2025-05-13 | 2025-05-15 | 2025-05-18 | 2025-05-18 | Done
|  | 6.3 | Deploy mobile app (beta) | Beta version released | Team | 3 | 2025-05-16 | 2025-05-18 | 2025-05-21 | 2025-05-21 | Done
|  | 6.4 | Fix deployment issues | Issue resolution report | Team | 3 | 2025-05-19 | 2025-05-21 | 2025-05-24 | 2025-05-24 | Done
|  | 6.5 | Release final version | Live mobile app | Team | 3 | 2025-05-22 | 2025-05-24 | 2025-05-27 | 2025-05-27 | Done
7 | Final Demonstration | 7.1 | Prepare presentation materials | Presentation slides | Team | 1 | 2025-05-25 | 2025-05-27 | 2025-05-30 | 2025-05-30 | Done
|  | 7.2 | Conduct demo for stakeholders | Live demonstration | Team | 1 | 2025-05-26 | 2025-05-28 | 2025-05-31 | 2025-05-31 | Done
|  | 7.3 | Gather final feedback | Feedback report | Team | 1 | 2025-05-27 | 2025-05-29 | 2025-06-01 | 2025-06-01 | Done
|  | 7.4 | Project closure & documentation | Final project report | Team | 1 | 2025-05-28 | 2025-05-30 | 2025-06-02 | 2025-06-02 | Done
Formulas:
Plan Start Date = [Plan Start Date, row above]+[MAY 22, 2025, row above]
Act StDate Started = [Act StDate Started, row above]+[MAY 22, 2025, row above]
PROJECT X- AUTOMATED = [PROJECT X- AUTOMATED, row above]+[MAY 22, 2025, row above]
Act End Date = [Act End Date, row above]+[MAY 22, 2025, row above]